FUTURE LINK CONSULTANTS

A way to career abroad

Offers, Discounts & Counsellor Wallet Module

DOCUMENT 5 OF 5 DEVELOPMENT SPRINT PLAN

Sequenced sprints, definition of done & UAT scenarios

Stack: React 18 + Vite + TypeScript + Supabase (PostgreSQL)

Version 1.0  •  Confidential  •  Verified against the current codebase

Amber boxes flag inferences not verifiable from the provided code.

# Table of Contents

# 1. Approach

This plan sequences the build so each sprint ships usable value and de-risks the next. It reflects the canonical Scope v2 status: much of the foundation exists, so early sprints are largely wiring rather than greenfield. Two-week sprints assumed; adjust to team capacity. Development is in Cursor against the existing Supabase + React codebase.

Developer priority #1 (from Scope §2.4 / §18) Wire wallet_topup_rules + Period Close achievement % → wallet sizing & unlocking. This single connection turns the existing manual wallet into the performance-linked wallet and unblocks most of the wallet value. It is front-loaded into Sprint 2–3.

# 2. Definition of Done (every story)

- Migration written, reversible, timestamped to match the existing 251 migrations.

- RLS policies added in the has_role pattern (per Permission Matrix); counsellor sees only own wallet.

- Money movements go through a SECURITY DEFINER function and write a wallet_ledger row.

- src/integrations/supabase/types.ts regenerated.

- Vitest unit tests for any wallet math (unlock, multiplier, funding split, clawback).

- Does not break invoice triggers, incentive-calculate-run, or credit_wallet (see API event map §7.1).

- Feature behind a flag if it changes existing live behaviour (e.g. unlock gating).

# 3. Sprint Breakdown

## Sprint 1 — Offer Lifecycle & Library

Goal: Add governance to the existing offers without breaking current screens.

- DB: ALTER offers (status, funding_source, contributions, branch_id, version, approved_by); add offer_status_history, offer_versions.

- Keep is_active in sync with status via trigger (backward compat with OffersAdmin/PortalOffers).

- Fn: fn_offer_set_status, fn_clone_offer; version-snapshot trigger.

- UI: extend /offers-admin with status widgets, filters, clone/archive/restore, version history.

- Deliverable: governed offer catalogue; existing pages keep working.

⚠ INFERENCE / TO CONFIRM: Existing pages read is_active. The sync trigger must be in place in the SAME migration that adds status, or current screens break.

## Sprint 2 — Wallet Sizing Wiring (Part 1)

Goal: Connect achievement and rules to wallet sizing (the priority wiring).

- DB: ALTER discount_wallets (assigned_target, base_wallet, performance_multiplier, potential_wallet, achieved_revenue, unlocked_amount); add wallet_multiplier_bands, wallet_unlock_rules.

- Fn: fn_size_wallet (reads wallet_topup_rules + bands), fn_unlocked_wallet.

- Sync achieved_revenue from incentive_runs (reuse, do not recompute).

- UI: Wallet Top-ups gains target + base + multiplier (read-only) + Auto-fund button.

- Deliverable: wallet auto-sizes from target and last-period score.

⚠ INFERENCE / TO CONFIRM: achieved_revenue must come from incentive-calculate-run output (net) — recomputing revenue here would double-count and conflict with safety rule R1.

## Sprint 3 — Proportional Unlock & Funding-Aware Spend (Part 2)

Goal: Gate spending by unlock and make deduction funding-aware.

- Fn: fn_apply_offer_discount wrapping the existing allocation path — add unlocked check + funding-source branch; keep the existing cap/balance trigger.

- UI: Give Discount shows potential/unlocked/spent/left + unlock bar; blocks over-unlock; approved-offer picker.

- Refund/clawback: reverse allocation + ledger credit-back; recalc achievement.

- Deliverable: earn-to-give wallet live end-to-end with correct funding maths.

⚠ INFERENCE / TO CONFIRM: Confirm the existing cap/balance trigger name before wrapping; wrap, don't replace, to keep the safety net.

## Sprint 4 — Performance Score & Period Close

Goal: Close the monthly loop with a real score.

- DB: counselor_performance_scores (or a view over incentive tables — see Schema flag).

- Fn: extend fn_close_due_wallets to compute score → multiplier → seed next wallet.

- UI: Period Close gains Score + Achv% columns; My Wallet dashboard (target, score, unlock projection, leaderboard rank).

- Deliverable: allocate → achieve → unlock → close → re-allocate cycle.

⚠ INFERENCE / TO CONFIRM: Score weights (40/20/20/10/10) are Business-Rules config, not hard-coded; read from a config table.

## Sprint 5 — Strategic Wallets & Restricted Builder

Goal: Ring-fenced wallets and safe self-serve offer types.

- Fn: enforce scope tags (scope_country_tag/scope_service_code/scope_master_key) at allocation time; spend-order config.

- DB: approved_offer_types; enforce in Give Discount / offer builder.

- UI: strategic wallet funding view; restricted builder hides waivers/scholarships for counsellors.

- Deliverable: management steering wallets + margin-safe counsellor offers.

⚠ INFERENCE / TO CONFIRM: Scope tags already exist on discount_wallets; this is enforcement + UI, not new schema.

## Sprint 6 — Promotion Requests, Calendar & Approvals

Goal: Field input and central planning.

- DB: promotion_requests, promotion_calendar.

- Fn: fn_promo_request_advance; approval routing by discount-depth matrix.

- UI: Request form + tracker; MarCom review queue; Promotions Calendar (month/quarter/annual); Approvals queue.

- Deliverable: controlled field input + single planning calendar.

## Sprint 7 — Channels & Distribution

Goal: Send offers across channels using existing infrastructure.

- Reuse whatsapp-send, email-send/smtp-send, telephony-click-to-call; link offer templates + tracking codes.

- Personalisation tokens; per-channel tracking into offer_events.

- UI: Channels & Templates; send from offer / from Give Discount.

- Deliverable: omni-channel delivery with attribution.

⚠ INFERENCE / TO CONFIRM: WhatsApp requires Meta-approved templates; reuse the DSH/whatsapp patterns and allow lead time for approval.

## Sprint 8 — Analytics & Influence Attribution

Goal: Prove ROI and long-term value.

- DB: offer_influence; Fn: fn_record_influence (direct/assisted/multi-service).

- Extend /offers-analytics (Recharts): ROI per offer, channel/branch/counsellor leaderboards, Wallet Impact Revenue, Offer Influence Revenue.

- Deliverable: full analytics + leaderboards (match formulas in API §10).

## Sprint 9 — AI Assistive Layer

Goal: Suggestions, drafting, and AI Offer Studio within guardrails.

- DB: ai_offer_suggestions; Fn: fn_suggest_offer (approved catalogue + wallet_ok).

- Edge: offer-ai-studio (admin/MarCom gated, ai-summarize auth pattern); reuse dsh-ai-generate-copy for drafts.

- UI: suggestion panel on lead/client; AI Offer Studio for MarCom; safe auto-send (L2) for birthday/festival.

- Deliverable: AI assists; counsellors never create offers; predictive/autonomous deferred.

# 4. Sprint Summary

| Sprint | Theme | Headline deliverable | Scope status |
| --- | --- | --- | --- |
| 1 | Offer lifecycle | Governed catalogue | ✅ base exists |
| 2 | Wallet sizing wiring | Auto-sized wallet | ✅ rules exist |
| 3 | Unlock + funding spend | Earn-to-give live | ✅ alloc exists |
| 4 | Score & period close | Monthly loop | ✅ close exists |
| 5 | Strategic + restricted | Steering + safe builder | ✅ tags exist |
| 6 | Requests + calendar | Field input + planning | 🔲 new |
| 7 | Channels | Omni-channel send | ✅ edge fns exist |
| 8 | Analytics | ROI + leaderboards | 🔲 extend |
| 9 | AI assistive | Suggestions + Studio | 🔲 new |

# 5. Rollout Sequencing

- Pilot branch first for Sprints 2–4 (wallet behaviour) before all-branch rollout.

- Feature flags: unlock-gating OFF until Sprint 3 verified; AI auto-send OFF until L1 trusted.

- Migration & rollout detail lives in the dedicated Migration & Rollout Plan.

# 6. UAT Scenarios

Acceptance scenarios that prove “done without errors” on real data. Each lists the steps and the expected result. Run on the pilot branch before sign-off.

### UAT-01: Full happy path

- Hot lead created; MarCom publishes an offer; counsellor sees it as eligible.

- Counsellor sends offer via WhatsApp; lead enrols; invoice raised with offer.

Expected: wallet_allocations debit recorded; wallet_ledger balance_after correct; offer_events redeemed; invoice totals unchanged by side-effects.

### UAT-02: Unlock gating

- Counsellor at 33% of target (₹1,00,000 of ₹3,00,000), potential wallet ₹15,000.

- Counsellor tries to give a ₹6,000 discount.

Expected: Only ~₹5,000 unlocked; the ₹6,000 attempt is blocked with remaining_unlocked shown.

### UAT-03: University-funded offer

- Apply a University-funded offer to a client's invoice.

Expected: No counsellor wallet deduction; allocation recorded for attribution; ledger shows zero debit.

### UAT-04: Joint-funded offer

- Apply a Joint offer (FL ₹2,000 / Univ ₹3,000).

Expected: Only ₹2,000 debits the counsellor wallet; ₹3,000 attributed to university.

### UAT-05: Counsellor blocked from AI Studio

- Counsellor navigates to /offers-ai-studio or calls offer-ai-studio.

Expected: 403 / not permitted; no AI offer creation possible.

### UAT-06: MarCom AI draft to library

- MarCom generates an offer pack, reviews, publishes.

Expected: Offer appears in offers_eligible_for_client; counsellor can then suggest/send it.

### UAT-07: Over-cap approval

- Counsellor requests an 18% discount (cap 10%).

Expected: Flagged exceeded_cap; routed to branch manager approval; not applied until approved.

### UAT-08: Scholarship needs admin

- Counsellor attempts a full fee waiver.

Expected: Blocked from self-serve; routes to admin-only approval.

### UAT-09: Period close sizing

- Run Period Close for a counsellor who hit 120% last period.

Expected: Score computed; 150% multiplier applied; next-period wallet = base × 1.5; rollover per policy.

### UAT-10: Refund reversal

- Refund an invoice that carried a wallet-funded offer.

Expected: Allocation reversed; ledger credit-back; redemption_count decremented; achievement recalced.

### UAT-11: Strategic wallet ring-fence

- Counsellor with a Germany-only strategic wallet tries to spend it on a UK client.

Expected: Blocked; strategic balance usable only on Germany-scoped offers/clients.

### UAT-12: Expired offer on invoice

- Attempt to redeem an offer past its valid_to on a new invoice.

Expected: Redemption rejected; offer not applied.

### UAT-13: Double claim prevented

- Client attempts to claim the same offer twice in the portal.

Expected: Second claim blocked by unique (client_id, offer_id).

### UAT-14: Concurrent spend

- Two near-simultaneous discounts from the same wallet that together exceed balance.

Expected: Row lock prevents overspend; one succeeds, the other is rejected.

### UAT-15: Empty wallet

- Counsellor with ₹0 wallet tries to give any discount.

Expected: Blocked; prompted to request top-up; no negative balance (unless allow_negative).

### UAT-16: Birthday auto-offer (safe auto-send)

- A client's birthday triggers offers-lifecycle-tick.

Expected: Personalised offer auto-sent on the approved safe-trigger; logged in offer_events.

### UAT-17: Wallet Impact vs total revenue

- Counsellor A hits target with little wallet use; B uses wallet heavily.

Expected: Wallet Impact Revenue reflects B's higher system usage; scoring rewards ROI, not raw discount.

### UAT-18: Branch scoping

- Manager views analytics and wallets.

Expected: Sees only their branch's data; cannot see other branches.

### UAT-19: credit_wallet not touched

- Apply a counsellor discount.

Expected: discount_wallets changes; credit_wallet (client loyalty) untouched.

### UAT-20: Types & build integrity

- After a schema migration, regenerate types and build.

Expected: Build passes; no type errors; existing invoice/incentive flows unaffected.

# 7. Sign-off

| Role | Name | Date | Approved |
| --- | --- | --- | --- |
| Technical lead |  |  | ☐ |
| Product / CRM admin |  |  | ☐ |
| Finance / Accounting |  |  | ☐ |
| Operations / Branch heads |  |  | ☐ |
| Business owner |  |  | ☐ |